## Startup Nonprofit Bus Plan
STARTUP NONPROFIT BUSINESS PLANNING TEMPLATE WITH TIMELINE
BUSINESS NAME |  | START DATE
2024-09-02
[5 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5
TASKS | TASK OWNER | START DATE | END DATE | # of Days | 2024-09-02 | 2024-09-03 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-30 | 2024-10-01 | 2024-10-02 | 2024-10-03 | 2024-10-04
Phase 1: Assess the Need |  | 2024-09-02 | 2024-09-04 | 3 | bar: 2024-09-02 to 2024-10-04
Clearly identify the problem and the solution |  | 2024-09-02 | 2024-09-03 | 2 | bar: 2024-09-02 to 2024-09-03
Research existing nonprofits addressing a similar idea |  | 2024-09-02 | 2024-09-02 | 1 | bar: 2024-09-02
Pinpoint gaps in existing services and programs |  | 2024-09-03 | 2024-09-03 | 1 | bar: 2024-09-03
Decide whether to proceed |  | 2024-09-04 | 2024-09-04 | 1 | bar: 2024-09-04
Phase 2: Find the Opportunity and Check Its Viability |  | 2024-09-05 | 2024-09-17 | 9 | bar: 2024-09-02 to 2024-10-04
Define your mission |  | 2024-09-05 | 2024-09-05 | 1 | bar: 2024-09-05
Research the market |  | 2024-09-05 | 2024-09-05 | 1 | bar: 2024-09-05
Conduct interviews with community leaders |  | 2024-09-06 | 2024-09-10 | 3 | bar: 2024-09-06 to 2024-09-10
Identify the resources you need |  | 2024-09-11 | 2024-09-13 | 3 | bar: 2024-09-11 to 2024-09-13
Identify your operating costs |  | 2024-09-13 | 2024-09-14 | 1 | bar: 2024-09-13
Determine your sources of funding |  | 2024-09-15 | 2024-09-15 | 0
Determine your fundraising methods |  | 2024-09-16 | 2024-09-17 | 2 | bar: 2024-09-16 to 2024-09-17
Phase 3: Evaluate Potential Risks |  | 2024-09-15 | 2024-09-23 | 6 | bar: 2024-09-02 to 2024-10-04
Assess the market size |  | 2024-09-15 | 2024-09-17 | 2 | bar: 2024-09-16 to 2024-09-17
Estimate your competition |  | 2024-09-17 | 2024-09-18 | 2 | bar: 2024-09-17 to 2024-09-18
Conduct a SWOT analysis |  | 2024-09-18 | 2024-09-19 | 2 | bar: 2024-09-18 to 2024-09-19
Assess the economic climate |  | 2024-09-19 | 2024-09-21 | 2 | bar: 2024-09-19 to 2024-09-20
Develop your strategic plan |  | 2024-09-22 | 2024-09-23 | 1 | bar: 2024-09-23
Phase 4: Attract Stakeholders |  | 2024-09-23 | 2024-10-01 | 7 | bar: 2024-09-02 to 2024-10-04
Seek strategic partnerships |  | 2024-09-23 | 2024-09-25 | 3 | bar: 2024-09-23 to 2024-09-25
Find volunteers and co-founders |  | 2024-09-26 | 2024-09-29 | 2 | bar: 2024-09-26 to 2024-09-27
Establish your outreach plan |  | 2024-09-29 | 2024-10-01 | 2 | bar: 2024-09-30 to 2024-10-01
Phase 5: Formalize the Organization |  | 2024-09-15 | 2024-09-19 | 4 | bar: 2024-09-02 to 2024-10-04
Form a board of directors |  | 2024-09-17 | 2024-09-18 | 2 | bar: 2024-09-17 to 2024-09-18
Formalize your procedures |  | 2024-09-15 | 2024-09-17 | 2 | bar: 2024-09-16 to 2024-09-17
Other |  | 2024-09-18 | 2024-09-19 | 2 | bar: 2024-09-18 to 2024-09-19
Phase 6: Establish Your Supporting Systems |  | 2024-09-17 | 2024-10-01 | 11 | bar: 2024-09-02 to 2024-10-04
Create your bookkeeping systems |  | 2024-09-17 | 2024-09-18 | 2 | bar: 2024-09-17 to 2024-09-18
Create your manuals and policies |  | 2024-09-19 | 2024-09-24 | 4 | bar: 2024-09-19 to 2024-09-24
Create your fundraising systems |  | 2024-09-23 | 2024-09-27 | 5 | bar: 2024-09-23 to 2024-09-27
Create a board portal to store key documents |  | 2024-09-30 | 2024-10-01 | 2 | bar: 2024-09-30 to 2024-10-01
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Business Plan Timeline
STARTUP NONPROFIT BUSINESS PLANNING TEMPLATE WITH TIMELINE
BUSINESS NAME |  | START DATE
2024-09-02
[5 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
TASKS | TASK OWNER | START DATE | END DATE | # of Days | time axis 2024-09-02 to 2025-01-17
Phase 1: Assess the Need |  | 0 | 0 | 0
Clearly identify the problem and solution |  |  |  | 0
Research existing nonprofits addressing similar idea |  |  |  | 0
Pinpoint gaps in existing services and programs |  |  |  | 0
Decide whether to proceed |  |  |  | 0
Phase 2: Find Opportunity and Check Viability |  | 0 | 0 | 0
Define your mission |  |  |  | 0
Research market |  |  |  | 0
Conduct interviews with community leaders |  |  |  | 0
Identify needed Resources |  |  |  | 0
Identify Operating Costs |  |  |  | 0
Determine Sources of Funding |  |  |  | 0
Determine Fundraising Methods |  |  |  | 0
Phase 3: Evaluate Potential Risks |  | 0 | 0 | 0
Assess Market Size |  |  |  | 0
Estimate Competition |  |  |  | 0
Conduct SWOT Analysis |  |  |  | 0
Assess Economic Climate |  |  |  | 0
Develop Strategic Plan |  |  |  | 0
Phase 4: Attract Stakeholders |  | 0 | 0 | 0
Seek Strategic Partnerships |  |  |  | 0
Find Volunteers and Co-Founders |  |  |  | 0
Establish Outreach Plan |  |  |  | 0
Phase 5: Formalize the Organization |  | 0 | 0 | 0
Form Board of Directors |  |  |  | 0
Formalize procedures |  |  |  | 0
Other |  |  |  | 0
Phase 6: Establish Supporting Systems |  | 0 | 0 | 0
Create bookkeeping systems |  |  |  | 0
Create Manuals and Policies |  |  |  | 0
Create fundraising systems |  |  |  | 0
Create board portal to store key documents |  |  |  | 0

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.