## Website 6-Step Redesign Project
WEBSITE 6-STEP REDESIGN PROJECT PLAN TEMPLATE
AT RISK | ACTION OR ITEM | DESCRIPTION | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
| 1) RESEARCH |  | Complete |  | 2024-01-18 | 2024-02-09 | 23 |  | Not Started
| – Current Site | Review the previous design process, assess the current website, and note what is and isn’t working. | Complete |  | 2024-01-18 | 2024-01-28 | 11 |  | Assigned
| – Competitor | Take the time to understand what your competitors are doing and assess if they’re doing it well. | Complete |  | 2024-01-18 | 2024-01-22 | 5 |  | In Progress
| – Customer | Examine your customers and prospect personas and their buying journey — this is a vital step in building the site architecture. | Complete |  | 2024-01-25 | 2024-01-28 | 4 |  | Under Review
| – Review and Approvals | Review all insights gathered from the research phase and get approval from stakeholders for the direction you want to go with the redesign. | Complete |  | 2024-01-27 | 2024-01-31 | 5 |  | Complete
| – Project Brief | Whether you are creating the site in house or using a vendor, create a brief that outlines what the site will look like before starting the planning phase. | Complete |  | 2024-01-30 | 2024-01-31 | 2 |  | On Hold
| – Vendor Selection (if applicable) | Review potential vendors, create and send out RFPs, and select a vendor. | Complete |  | 2024-02-01 | 2024-02-09 | 9
| 2) PLAN |  | In Progress |  | 2024-02-11 | 2024-03-29 | 48
| – Strategy and Goals | Develop and write a plan that keeps business goals and KPIs in mind. Create a deck for the team to review and approve. | In Progress |  | 2024-02-11 | 2024-02-28 | 18
| – Brand Guidelines | If you don’t have or haven’t recently refreshed brand guidelines, do so in this phase. | Assigned |  | 2024-02-22 | 2024-02-27 | 6
| – Content | Create a content plan and architecture. Identifying a content plan before entering the design phase makes it easier to create a site plan and wireframe. | Assigned |  | 2024-02-23 | 2024-02-26 | 4
| – Timeline | Set up a start-to-finish schedule. | Under Review |  | 2024-02-25 | 2024-02-27 | 3
| – Assign Responsibilities | Determine internal and external stakeholders and assign them responsibilities to ensure communication throughout the process. | On Hold |  | 2024-02-28 | 2024-03-04 | 6
| – Assemble All Components | Combine all of the planning documents into a single document. | On Hold |  | 2024-03-11 | 2024-03-20 | 10
| – Approvals | Make sure there is a stakeholder review and that you secure approvals of all planning items before the design process begins. | On Hold |  | 2024-03-17 | 2024-03-29 | 13
| 3) DESIGN |  | Assigned |  | 2024-03-29 | 2024-05-23 | 56
| – Mood Boards | Employ look-and-feel visuals to convey the colors, photos, videos, graphic style, layout, and copy tone. Check that the board aligns with your brand. | Assigned |  | 2024-03-29 | 2024-04-03 | 6
| – Sitemap | This visual describes the relationships between the main areas of your website in order to illustrate usability in the final product. The sitemap makes it possible to build a user friendly and easily navigable website. | Assigned |  | 2024-04-04 | 2024-04-15 | 12
| – Wireframes | Create the home page first. Then add all the sub-pages using the website hierarchy previously created in the sitemap. | Not Started |  | 2024-04-19 | 2024-05-01 | 13
| – Page Layout | The primary functions of a layout are to show the information structure, help you visualize content, and allow you to demonstrate basic functionality. Designs contain colors, logos, and images to help you preview the future product. | Not Started |  | 2024-05-02 | 2024-05-10 | 9
| – Select Technologies | Select the appropriate technology stack – i.e., programming language(s), frameworks, and CMS — to ensure that the server can handle the installation and that the setup is friction-free. | Not Started |  | 2024-05-03 | 2024-05-20 | 18
| – Approvals | Review and approve everything decided upon during the design phase. Adherence to the plan will prevent additional costs and scope creep. | Not Started |  | 2024-05-20 | 2024-05-23 | 4
| 4) DEVELOP |  | Not Started |  | 2024-05-25 | 2024-06-11 | 18
| – Coding | Test static web page elements designed during the mock-up and layout stage. Add special features and interactivity. | Not Started |  | 2024-05-25 | 2024-05-30 | 6
| – Deploy | Implement frameworks and CMS to ensure the server can handle installation and setup. Upload the site to the server using FTP (file transfer protocol) software. | Not Started |  | 2024-05-27 | 2024-06-07 | 12
| – SEO | Optimize website elements to help your site achieve higher search engine rankings. Valid code is essential for successful SEO. | Not Started |  | 2024-06-06 | 2024-06-11 | 6
| 5) QA AND LAUNCH |  | Not Started |  | 2024-06-14 | 2024-06-25 | 12
| – Test | This is the time for user testing, technical testing, and A/B testing on a variety of platforms (multiple browsers, mobile devices, and OSs) to ensure functionality. After deployment, run a final test to ensure the correct file installation. | Not Started |  | 2024-06-14 | 2024-06-20 | 7
| – Regression Test and Launch | Confirm that the new programs or code changes haven’t adversely affected existing features. Upload and launch the site. | Not Started |  | 2024-06-21 | 2024-06-25 | 5
| 6) ITERATE |  | Not Started |  | 2024-06-26 | 2024-07-15 | 20
| – Maintenance | Ensure inks, forms, scripts, video, and code are all valid. It’s also a good time to spell-check all the latest content. | Not Started |  | 2024-06-26 | 2024-06-30 | 5
| – Opinion Monitoring and Ongoing Attention to Analytics | Review customer feedback systems and check in with your help desk and other personnel. Check analytics tools to gather more insights. | Not Started |  | 2024-07-01 | 2024-07-07 | 7
| – Regular Updating | Fix and refresh the site based on technical and user feedback. | Not Started |  | 2024-07-07 | 2024-07-15 | 9
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
START DATE = MIN([START DATE, row below]:G9)
END DATE = MAX([END DATE, row below]:H9)

## BLANK - Website 6-Step Redesign
WEBSITE 6-STEP REDESIGN PROJECT PLAN TEMPLATE
AT RISK | ACTION OR ITEM | DESCRIPTION | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
| 1) RESEARCH |  |  |  | 0 | 0 |  |  | Not Started
| – Current Site | Review the previous design process, assess the current website, and note what is and isn’t working. | [6 empty] | Assigned
| – Competitor | Take the time to understand what your competitors are doing and assess if they’re doing it well. | [6 empty] | In Progress
| – Customer | Examine your customers and prospect personas and their buying journey — this is a vital step in building the site architecture. | [6 empty] | Under Review
| – Review and Approvals | Review all insights gathered from the research phase and get approval from stakeholders for the direction you want to go with the redesign. | [6 empty] | Complete
| – Project Brief | Whether you are creating the site in house or using a vendor, create a brief that outlines what the site will look like before starting the planning phase. | [6 empty] | On Hold
| – Vendor Selection (if applicable) | Review potential vendors, create and send out RFPs, and select a vendor.
| 2) PLAN |  |  |  | 0 | 0
| – Strategy and Goals | Develop and write a plan that keeps business goals and KPIs in mind. Create a deck for the team to review and approve.
| – Brand Guidelines | If you don’t have or haven’t recently refreshed brand guidelines, do so in this phase.
| – Content | Create a content plan and architecture. Identifying a content plan before entering the design phase makes it easier to create a site plan and wireframe.
| – Timeline | Set up a start-to-finish schedule.
| – Assign Responsibilities | Determine internal and external stakeholders and assign them responsibilities to ensure communication throughout the process.
| – Assemble All Components | Combine all of the planning documents into a single document.
| – Approvals | Make sure there is a stakeholder review and that you secure approvals of all planning items before the design process begins.
| 3) DESIGN |  |  |  | 0 | 0
| – Mood Boards | Employ look-and-feel visuals to convey the colors, photos, videos, graphic style, layout, and copy tone. Check that the board aligns with your brand.
| – Sitemap | This visual describes the relationships between the main areas of your website in order to illustrate usability in the final product. The sitemap allows you to build a user friendly and easily navigable website.
| – Wireframes | Create the home page first. Then add all the sub-pages using the website hierarchy previously created in the sitemap.
| – Page Layout | The primary functions of a layout are to show the information structure, help you visualize content, and allow you to demonstrate basic functionality. Designs contain colors, logos, and images to help you preview the future product.
| – Select Technologies | Select the appropriate technology stack – i.e., programming language(s), frameworks, and CMS — to ensure that the server can handle the installation and that the setup is friction-free.
| – Approvals | Review and approve everything decided upon during the design phase. Adherence to the plan will prevent additional costs and scope creep.
| 4) DEVELOP |  |  |  | 0 | 0
| – Coding | Test static web page elements designed during the mock-up and layout stage. Add special features and interactivity.
| – Deploy | Implement frameworks and CMS to ensure the server can handle installation and setup. Upload the site to the server using FTP (file transfer protocol) software.
| – SEO | Optimize website elements to help your site achieve higher search engine rankings. Valid code is essential for successful SEO.
| 5) QA AND LAUNCH |  |  |  | 0 | 0
| – Test | This is the time for user testing, technical testing, and A/B testing on a variety of platforms (multiple browsers, mobile devices, and OSs) in order to ensure functionality. After deployment, run a final test to ensure the correct file installation.
| – Regression Test and Launch | Confirm that the new programs or code changes haven’t adversely affected existing features. Upload and launch the site.
| 6) ITERATE |  |  |  | 0 | 0
| – Maintenance | Ensure inks, forms, scripts, video, and code are all valid. It’s also a good time to spell-check all the latest content.
| – Opinion Monitoring and Ongoing Attention to Analytics | Review customer feedback systems and check in with your help desk and other personnel. Check analytics tools to gather more insights.
| – Regular Updating | Fix and refresh the site based on technical and user feedback.
Formulas:
START DATE = MIN([START DATE, row below]:G9)
END DATE = MAX([END DATE, row below]:H9)
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.