## Roles & Responsibilities - EX
ROLES AND RESPONSIBILITIES TEMPLATE
PROJECT
Launch new website
DESCRIPTION
Update site with new look and feel
R Responsible A Accountable C Consulted I Informed
NAME | [ TEAM MEMBER NAME ] | [ TEAM MEMBER NAME ] | [ TEAM MEMBER NAME ] | [ TEAM MEMBER NAME ]
ROLE | CONTENT | DESIGNER | DEV | PM
PROJECT DELIVERABLE / ACTIVITY
PHASE 1: PROJECT PLANNING | [5 empty] | RACI KEY
Research | C | I | I | R | R | Responsible
Interviews | A | C | C | I | A | Accountable
Wireframe | R | C | I | A | C | Consulted
PHASE 2: DEVELOPMENT |  |  |  |  | I | Informed
Provide Imagery | A | R | C | I
Systems Design | A | R | R | I
Systems Analysis and Requirements | A | A | R | C
CLICK HERE TO CREATE IN SMARTSHEET

## Roles & Responsibilities BLANK
ROLES AND RESPONSIBILITIES TEMPLATE
PROJECT
DESCRIPTION
R Responsible A Accountable C Consulted I Informed | – Insert Image – | – Insert Image – | – Insert Image – | – Insert Image –
NAME | [ TEAM MEMBER NAME ] | [ TEAM MEMBER NAME ] | [ TEAM MEMBER NAME ] | [ TEAM MEMBER NAME ]
ROLE | [ TEAM MEMBER ROLE ] | [ TEAM MEMBER ROLE ] | [ TEAM MEMBER ROLE ] | [ TEAM MEMBER ROLE ]
PROJECT DELIVERABLE / ACTIVITY
Initiate Phase Activities | [5 empty] | RACI KEY
Request Review by PMO |  |  |  |  | R | Responsible
Submit Project Request |  |  |  |  | A | Accountable
Research Solution |  |  |  |  | C | Consulted
Develop Business Case |  |  |  |  | I | Informed
Plan Phase Activities
Create Project Charter
Create Schedule
Create Add'l Plans as Required
Execute Phase Activities
Build Deliverables
Create Status Report
Control Phase Activities
Perform Change Management
Close Phase Activities
Create Lessons Learned
Create Project Closure Report

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.