## Agile RACI Matrix by Assignment
AGILE RACI MATRIX BY ASSIGNMENT TEMPLATE
PROJECT TITLE | [8 empty] | PROJECT MANAGER
Mission to Complete the Thing We Need to Do | [8 empty] | Alia
|  | R | A | C | I
READY TO START? | TASK DESCRIPTION | RESPONSIBLE | ACCOUNTABLE | CONSULTED | INFORMED | % of PROGRESS | DUE DATE | STATUS | NOTES
Yes | INITIATE PHASE ACTIVITIES |  |  |  |  | 38.75% | 00/00/00 | In Progress
Yes | Request Review by PMO | Alia |  | Rachel | Ian + Carl | 80% | 00/00/00 | Needs Review
No | Submit Project Request | Alia |  | Rachel | Ian + Carl | 50% |  | In Progress
Yes | Research Solution |  | Rachel | Ian + Carl | Alia | 20% |  | Approved
No | Develop Business Case | Rachel | Alia | Carl | Ian | 5% |  | Overdue
Yes | PLAN PHASE ACTIVITIES |  |  |  |  | 33.33% |  | On Hold
Yes | Create Project Charter | Ian | Rachel | Carl | Alia | 100% |  | Complete
No | Create Schedule | Carl | Rachel |  | Alia | 0% |  | Not Started
No | Create Additional Plans as Required | Carl | Rachel + Ian | Alia |  | 0% |  | On Hold
No | EXECUTE PHASE ACTIVITIES |  |  |  |  | 0%
No | Build Deliverables |  |  |  |  | 0%
No | Create Status Report |  |  |  |  | 0%
No | CONTROL PHASE ACTIVITIES |  |  |  |  | 0%
No | Perform Change Management |  |  |  |  | 0%
No | CLOSE PHASE ACTIVITIES |  |  |  |  | 0%
No | Create Lessons Learned |  |  |  |  | 0%
No | Create Project Closure Report |  |  |  |  | 0%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Agile RACI Matrix
AGILE RACI MATRIX BY ASSIGNMENT
PROJECT TITLE | [8 empty] | PROJECT MANAGER
|  | R | A | C | I
READY TO START? | TASK DESCRIPTION | RESPONSIBLE | ACCOUNTABLE | CONSULTED | INFORMED | % of PROGRESS | DUE DATE | STATUS | NOTES
Yes | [7 empty] | Not Started
No | [7 empty] | In Progress
Complete
Needs Review
Approved
Overdue
On Hold

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.