## EXAMPLE - IT Change Request
IT CHANGE REQUEST FORM TEMPLATE – EXAMPLE
Organization | Panel Power |  | Request Number | 1012
Department | Customer Service |  | Date Requested | 02/28/20XX
Attachments | N/A |  | Date Needed | 03/15/20XX
Requester's Name and Title | Steve Frazier, Customer Service Manager | Requester's Email
Manager's Name | Michael Schwartz | Manager's Email
REQUEST DETAILS
Change Description | I am requesting the implementation of a new customer relationship management system.
Change Reason | The current system lacks the ability to track customer interactions efficiently.
Associated Incidences | N/A
Location | N/A |  | Priority | Medium
Attachments | N/A |  | Change Type | Normal
IMPACTS
Service Impact | The system will improve customer interactions and enhance data management.
CI Impact | A CI analyst will need to manage, track, and document the software's data.
Budget Impact | We must increase the budget in order to license and maintain the software and train users.
Scope Impact | The scope must increase to include system implementation and user training.
Timeline Impact | We must extend the timeline in accordance with the complexity of the system to allow for in-depth testing and user training.
Resources Impact | Implementing the new system will impact the following resources: IT personnel, training, budget, quality assurance, and testing.
RISK
Risk Analysis | Potential problems concern user adoption, integration with existing systems, and budget overruns.
Change Advisory Board (CAB) / Emergency Change Advisory Board (ECAB) Decision
CAB Decision
CAB Comments
ECAB Decision
ECAB Comments
DECISION
Name |  |  | Date | 00/00/0000
Title |  |  | Decision | APPROVED
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - IT Change Request Form
IT CHANGE REQUEST FORM TEMPLATE
IT CHANGE REQUEST FORM
Organization |  | Request Number
Department |  | Date Requested
Attachments |  | Date Needed
Requester's Name and Title | Requester's Email
Manager's Name | Manager's Email
REQUEST DETAILS
Change Description
Change Reason
Associated Incidences
Location |  | Priority
Attachments |  | Change Type
IMPACTS
Service Impact
CI Impact
Budget Impact
Scope Impact
Timeline Impact
Resources Impact
RISK
Risk Analysis
Change Advisory Board (CAB) / Emergency Change Advisory Board (ECAB) Decision
CAB Decision
CAB Comments
ECAB Decision
ECAB Comments
DECISION
Name |  | Date
Title |  | Decision

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
PRIORITY | CHANGE TYPE | APPROVAL STATUS
Low | Normal | APPROVED
Medium | Standard | DENIED
High | Emergency

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.