## EXAMPLE - ABM Campaign
ACCOUNT-BASED MARKETING (ABM) CAMPAIGN EXAMPLE
CAMPAIGN TITLE |  | PROJECT MANAGER | START DATE | END DATE
Positive Charge ABM Campaign |  | Marta Hicks | 00/00/00 | 00/00/00
PHASES AND ACTIVITIES | STATUS | ASSIGNED TO | START DATE | END DATE | NOTES
PHASE 1: Account Selection and Segmentation
Identify High-Value Prospects | Complete | Eliezer Ola | 2031-01-16 | 2031-02-02 | Focus on organizations with large fleets or establishments in regions with high EV adoption rates.
Do Market Research for EV Needs | In Progress | Helen Bates | 2031-01-31 | 2031-02-05 | Analyze areas with a rising demand for EV charging, including city centers, travel hubs, and business districts.
Prioritize Accounts by Revenue Potential | Not Started | Jose Price | 2031-02-05 | 2031-02-15 | Rank prospects based on potential charging volume, scalability, and long-term partnership opportunities.
Do Geographic Targeting | Overdue | Kishore Kramer | 2031-01-22 | 2031-01-29 | Pinpoint locations with minimal charging infrastructure but a growing number of EV registrations.
Do Industry Trend Analysis | Needs Review | Marta Hicks | 2031-01-28 | 2031-01-31 | Examine global and regional trends in EV adoption to anticipate future demand and expansion possibilities.
PHASE 2: Targeted Content Creation
Create EV Infrastructure Whitepapers | Approved
Share Benefits of Positive Charge Infographics | On Hold
Create Customized Video Testimonials
Create ROI Calculators for EV Charging
Transition to EV eBooks
PHASE 3: Multi-Channel Engagement
Run LinkedIn Targeted Ads
Do Email Drip Campaigns
Send Webinar Invitations
Retarget Ads on Industry Websites
Run Sponsored Content on EV Blogs
PHASE 4: Personalized Outreach and Events
Do VIP Demos of Positive Charge Products
Host Exclusive Webinars for Key Decision-Makers
Offer Positive Charge Facility Tours
Write Custom Proposals and Pitches
Host EV Industry Roundtables
PHASE 5: Measurement and Analytics
Track Website Engagement
Share Email Campaign Effectiveness Reports
Share ROI Measurement for Each Account
Share Social Media Engagement Metrics
Track Conversion Rate
PHASE 6: Post-Engagement Nurturing and Expansion
Host Follow-Up Webinars
Schedule Quarterly Review Meetings
Issue Feedback Surveys
Give Exclusive Offers to Early Adopters
Launch Referral Program
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - ABM Campaign
ACCOUNT-BASED MARKETING (ABM) CAMPAIGN TEMPLATE
CAMPAIGN TITLE |  | PROJECT MANAGER | START DATE | END DATE
PHASES AND ACTIVITIES | STATUS | ASSIGNED TO | START DATE | END DATE | NOTES
PHASE 1:
PHASE 2:
PHASE 3:
PHASE 4:
PHASE 5:
PHASE 6:

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.