## EXAMPLE Critical Path Chart
Critical Path Chart Template Example
Establishing a Nationwide Cybersecurity Awareness Program
ID | PREDECESSOR ACTIVITIES enter separately in columns | [5 empty] | DURATION in days | ACTIVITY DESCRIPTION
A | - | - | - | - | - | - | 10 | Project Initiation
B | A | [5 empty] | 15 | Stakeholder Analysis
C | B | [5 empty] | 10 | Program Goals Definition
D | C | [5 empty] | 20 | Budget Approval
E | C | [5 empty] | 30 | Curriculum Development
F | E | [5 empty] | 20 | Pilot Program Design
G | D | [5 empty] | 25 | Hiring of Trainers and Staff
H | D | [5 empty] | 40 | IT Infrastructure Setup
I | E | [5 empty] | 45 | Development of Online Resources
J | C | [5 empty] | 25 | Marketing and Public Relations Plan
K | F | G | H | I |  |  | 15 | Pilot Program Launch
L | K | [5 empty] | 20 | Pilot Program Review and Feedback Analysis
M | L | [5 empty] | 30 | Full Program Rollout Planning
N | M | [5 empty] | 50 | Implementation of Full Program
CRITICAL PATH EXAMPLE
Use red arrows to illustrate the critical path.
CLICK HERE TO CREATE IN SMARTSHEET
ACTIVITY ID
–––––––––––
DURATION IN DAYS
A
–––––––
10
B
–––––––
15
C
–––––––
10
E
–––––––
30
I
–––––––
45
D
–––––––
20
START
FINISH
G
–––––––
25
H
–––––––
40
M
–––––––
30
J
–––––––
25
F
–––––––
20
L
–––––––
20
K
–––––––
15
N
–––––––
6
X
–––––––
X
X
–––––––
X

## BLANK Critical Path Chart
Critical Path Chart Template
ID | PREDECESSOR ACTIVITIES enter separately in columns | [5 empty] | DURATION in days | ACTIVITY DESCRIPTION
A | - | - | - | - | - | - | 2 | Activity 1
B | A | [5 empty] | 4 | Activity 2
C | B | [5 empty] | 10 | Activity 3
D | C | [5 empty] | 6 | Activity 4
E | C | [5 empty] | 4 | Activity 5
F | E | [5 empty] | 5 | Activity 6
G | D | [5 empty] | 7 | Activity 7
H | E | G |  |  |  |  | 9 | Activity 8
I | C | [5 empty] | 7 | Activity 9
J | F | I |  |  |  |  | 8 | Activity 10
K | J | [5 empty] | 4 | Activity 11
L | J | [5 empty] | 5 | Activity 12
M | H | [5 empty] | 2 | Activity 13
N | K | L |  |  |  |  | 6 | Activity 14
CRITICAL PATH
Use red arrows to illustrate the critical path.
ACTIVITY ID
–––––––––––
DURATION IN DAYS
A
–––––––
2
B
–––––––
4
C
–––––––
10
E
–––––––
4
I
–––––––
7
D
–––––––
6
START
FINISH
G
–––––––
7
H
–––––––
9
M
–––––––
2
J
–––––––
8
F
–––––––
5
L
–––––––
5
K
–––––––
4
N
–––––––
6
X
–––––––
X
X
–––––––
X

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.