## EXAMPLE - Sales Enablement
Sales Enablement GTM Plan Example
Executive Summary
Prime Financial Software provides cutting-edge financial software solutions for businesses. We are launching Cloud Ledger, a cloud-based accounting platform designed to streamline financial management and reporting for small to medium-sized enterprises. By implementing a comprehensive sales enablement GTM strategy, we aim to equip our sales team with the knowledge, tools, and resources needed to effectively promote and sell Cloud Ledger.
TASK TITLE | TASK DESCRIPTION | ASSIGNED OWNER | DUE DATE | TASK STATUS
MARKET ANALYSIS | Evaluate the market potential and value specifically for cloud-based accounting solutions targeting small to medium-sized businesses (SMBs). | Alexandra Mattson | MM/DD/YY | In Progress
| Conduct a detailed competitor analysis focusing on feature comparisons, pricing strategies, and customer satisfaction levels of existing cloud accounting platforms. | Alexandra Mattson | MM/DD/YY | Not Started
| Define the target audience by identifying the primary decision-makers within SMBs, such as financial managers, CFOs, and business owners, who are responsible for purchasing accounting software. | Aviv Perez | MM/DD/YY | Complete
AUDIENCE PERSONAS | Create customer surveys tailored to SMB owners and financial managers to understand their needs, pain points, and decision-making processes regarding accounting software. | Aviv Perez | MM/DD/YY | Complete
| Conduct phone interviews with financial managers, CFOs, and business owners to gain deeper insights into their specific requirements, challenges, and expectations. | Brian Gorman | MM/DD/YY | In Progress
| Collect and analyze data from web and social analytics focusing on SMB engagement to identify trends, preferences, and behaviors related to accounting software solutions. | Brooklyn Jansen | MM/DD/YY | In Progress
| Develop detailed buyer personas based on the collected data, including demographic information, job roles, goals, challenges, and preferred communication channels. | Aviv Perez | MM/DD/YY | Not Started
| Map out the typical customer journeys for each buyer persona, identifying key touchpoints and opportunities for engagement throughout the sales process. | Aviv Perez | MM/DD/YY | Not Started
PRODUCT PRICING | Outline business goals related to revenue targets, market penetration, and customer acquisition costs. | Devon Gomez | MM/DD/YY | In Progress
| Conduct a detailed analysis of competitor pricing models, including subscription tiers, feature sets, and perceived value, to benchmark Cloud Ledger’s pricing strategy effectively. | Alexandra Mattson | MM/DD/YY | Not Started
| Determine the comprehensive costs associated with Cloud Ledger, including development, maintenance, customer support, and marketing expenses, to establish a sustainable pricing model. | Devon Gomez | MM/DD/YY | In Progress
| Create tiered pricing options that cater to different segments of SMBs, offering various levels of features and services to meet diverse customer needs and maximize market reach. | Devon Gomez | MM/DD/YY | Not Started
MARKET POSITIONING | Define Cloud Ledger’s unique value proposition by highlighting key differentiators such as advanced features, ease of use, integration capabilities, and specific benefits tailored to SMBs. | Diana Kennedy | MM/DD/YY | In Progress
| Create a compelling positioning statement that succinctly communicates Cloud Ledger’s unique value and competitive advantages to target audiences, emphasizing its impact on improving financial management for SMBs. | Diana Kennedy | MM/DD/YY | In Progress
| Finalize a comprehensive messaging framework that includes key messages, proof points, and supporting data, ensuring consistency across all marketing and sales communications. | Diana Kennedy | MM/DD/YY | Not Started
| Identify and prioritize key market segments within the SMB space that would benefit the most from Cloud Ledger’s features and tailor the positioning strategy to resonate with these segments. | Alexandra Mattson | MM/DD/YY | Not Started
GO-TO-MARKET STRATEGY | Outline a sales enablement strategy that includes tools, resources, and support needed to empower the sales team to effectively sell Cloud Ledger, focusing on understanding customer needs and demonstrating product value. | Brian Gorman | MM/DD/YY | In Progress
| Develop a comprehensive marketing plan that aligns with the sales strategy, incorporating content marketing, social media campaigns, webinars, and targeted advertising to generate and nurture leads. | Diana Kennedy | MM/DD/YY | Not Started
| Create detailed plans for sales training, lead generation, content creation, and performance metrics to ensure a cohesive and actionable strategy. | Brian Gorman | MM/DD/YY | Not Started
SALES ENABLEMENT | Develop in-depth training content, including product overviews, feature demonstrations, competitive positioning, and sales scripts, to ensure the sales team is well-equipped to sell Cloud Ledger. | Brian Gorman | MM/DD/YY | In Progress
| Organize and conduct training sessions, both online and in-person, to provide hands-on experience with Cloud Ledger and ensure the sales team can effectively address customer queries and objections. | Brian Gorman | MM/DD/YY | Not Started
| Develop a series of email templates tailored to different stages of the sales funnel, from initial outreach to follow-up and closing, enabling the sales team to maintain consistent and personalized communication with prospects. | Diana Kennedy | MM/DD/YY | Not Started
| Develop and distribute sales playbooks that include detailed strategies, best practices, and step-by-step guides to navigate the sales process for Cloud Ledger, ensuring sales team members have a clear roadmap to follow. | Brian Gorman | MM/DD/YY | In Progress
EXTERNAL LAUNCH | Complete a detailed crisis management plan before the launch, outlining potential risks, response strategies, communication protocols, and responsible personnel to ensure quick and effective handling of any issues that arise. | Devon Gomez | MM/DD/YY | Not Started
| Follow the integrated marketing plan meticulously, ensuring that all planned activities, including content releases, social media campaigns, and promotional events, are executed on schedule to maximize visibility and lead generation for Cloud Ledger. | Diana Kennedy | MM/DD/YY | On Hold
| Keep all relevant stakeholders, including investors, partners, and key customers, informed about any issues, updates, or changes related to the launch. | Aviv Perez | MM/DD/YY | On Hold
METRICS | Regularly monitor and analyze the performance of various marketing channels, including social media, email campaigns, webinars, and paid advertising, to understand their effectiveness in driving engagement and generating leads for Cloud Ledger. | Brooklyn Jansen | MM/DD/YY | On Hold
| Monitor the percentage of leads that are successfully converted into paying customers by the sales team, providing insight into the effectiveness of sales enablement efforts. | Brooklyn Jansen | MM/DD/YY | On Hold
| Track the average time taken to convert a lead into a customer, identifying any bottlenecks or areas for improvement in the sales process. | Brooklyn Jansen | MM/DD/YY | On Hold
| Develop and maintain regular reports on key performance indicators (KPIs) such as lead conversion rates, customer acquisition costs, and return on investment (ROI), providing actionable insights for the sales and marketing teams. | Brooklyn Jansen | MM/DD/YY | On Hold
POST-LAUNCH FEEDBACK | Create and distribute a comprehensive post-launch survey to customers who have adopted Cloud Ledger, gathering feedback on their experience, satisfaction, and any issues encountered to identify areas for improvement. | Brian Gorman | MM/DD/YY | On Hold
| Complete detailed win/loss interviews with recent customers and lost prospects to understand the reasons behind their decisions, providing valuable insights into the effectiveness of the sales process and areas for refinement. | Brian Gorman | MM/DD/YY | On Hold
| Organize a post-launch review meeting with key stakeholders, including the sales, marketing, product, and customer support teams, to discuss feedback, analyze performance data, and develop actionable plans for ongoing optimization and future launches. | Aviv Perez | MM/DD/YY | On Hold
| Based on post-launch feedback, update and refine sales enablement materials, training content, and playbooks to address any identified gaps and enhance the sales team’s effectiveness in future engagements. | Brian Gorman | MM/DD/YY | On Hold
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Sales Enablement GTM
Sales Enablement GTM Plan
Executive Summary
Description
TASK TITLE | TASK DESCRIPTION | ASSIGNED OWNER | DUE DATE | TASK STATUS
MARKET ANALYSIS | Description | Name | MM/DD/YY | In Progress
| Description | Name | MM/DD/YY | Not Started
| Description | Name | MM/DD/YY | Complete
AUDIENCE PERSONAS | Description | Name | MM/DD/YY | Complete
|  |  | MM/DD/YY | In Progress
|  |  | MM/DD/YY | In Progress
|  |  | MM/DD/YY | Not Started
|  |  | MM/DD/YY | Not Started
PRODUCT PRICING |  |  | MM/DD/YY | In Progress
|  |  | MM/DD/YY | Not Started
|  |  | MM/DD/YY | In Progress
|  |  | MM/DD/YY | Not Started
MARKET POSITIONING |  |  | MM/DD/YY | In Progress
|  |  | MM/DD/YY | In Progress
|  |  | MM/DD/YY | Not Started
|  |  | MM/DD/YY | Not Started
GO-TO-MARKET STRATEGY |  |  | MM/DD/YY | In Progress
|  |  | MM/DD/YY | Not Started
|  |  | MM/DD/YY | Not Started
SALES ENABLEMENT |  |  | MM/DD/YY | In Progress
|  |  | MM/DD/YY | Not Started
|  |  | MM/DD/YY | Not Started
|  |  | MM/DD/YY | In Progress
EXTERNAL LAUNCH |  |  | MM/DD/YY | Not Started
|  |  | MM/DD/YY | On Hold
|  |  | MM/DD/YY | On Hold
METRICS |  |  | MM/DD/YY | On Hold
|  |  | MM/DD/YY | On Hold
|  |  | MM/DD/YY | On Hold
|  |  | MM/DD/YY | On Hold
POST-LAUNCH FEEDBACK |  |  | MM/DD/YY | On Hold
|  |  | MM/DD/YY | On Hold
|  |  | MM/DD/YY | On Hold
|  |  | MM/DD/YY | On Hold

## Status Keys - DO NOT DELETE
STATUS KEY
Not Started
In Progress
Complete
On Hold
Overdue
Needs Review

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.