## Agile Sprint Capacity Planning
Agile Sprint Capacity Planning Template
SPRINT SUMMARY |  | Summary data populates automatically
STAGE TOTALS |  | STATUS TOTALS
Not Started | 10 | Green | 7
In Progress | 4 | Amber | 2
Complete | 3 | Red | 2
On Hold | 0 | Grey | 14
Overdue | 2
Needs Review | 2
Blocked | 2
Testing | 2
SPRINT | STORY OR TASK | EPIC | TYPE | DESCRIPTION | STAGE | STATUS | STORY POINTS | POINTS CAPACITY | POINTS AVAILABLE | ASSIGNED TO | COMMENTS | START DATE | FINISH DATE | STAGE KEY | STATUS KEY
| Release 1 (R1) |  | Release |  |  |  | 47 | 300 | 259 |  |  |  |  | Not Started | Green
Sprint 1 (R1) | Sprint 1 (R1) | [5 empty] | 35 | 75 | 40 |  |  |  |  | In Progress | Amber
Sprint 1 (R1) | Search for other employees | Epic 1 | Story | As an employee I want to search for other employees using their last name so that I can easily contact any colleague. | In Progress | Green | 21 | [6 empty] | Complete | Red
Sprint 1 (R1) | Code the ... | Epic 1 | Task | <Describe the work needed to complete.> | Blocked | Red | 8 |  |  | Anthony Gruenelli | We are blocked on coding until all team resources have access. |  |  | On Hold | Grey
Sprint 1 (R1) | Design the ... | Epic 1 | Task | <Describe the work needed to complete.> | In Progress | Amber | 5 |  |  | Cari Franklin | Designs are in progress. Additional design prototypes could require additional funding. |  |  | Overdue
Sprint 1 (R1) | Add options to ... | Epic 1 | Task | <Describe the work needed to complete.> | Testing | Green | 6 |  |  | Hiro Senjima | Testing is in progress |  |  | Needs Review
Sprint 1 (R1) | Integrate with ... | Epic 1 | Task | <Describe the work needed to complete.> | Complete | Green | 2 |  |  | Alex Bright | All integration points are coded and tested. |  |  | Blocked
Sprint 1 (R1) | Bulk add users | Epic 2 | Story |  | In Progress | Green | 14 | [6 empty] | Testing
Sprint 1 (R1) | <Task> | Epic 2 | Task | <Describe the work needed to complete.> | In Progress | Green | 4
Sprint 1 (R1) | <Task> | Epic 2 | Task | <Describe the work needed to complete.> | Testing | Amber | 2
Sprint 1 (R1) | <Task> | Epic 2 | Task | <Describe the work needed to complete.> | Complete | Green | 4
Sprint 1 (R1) | <Task> | Epic 2 | Task | <Describe the work needed to complete.> | Complete | Green | 3
Sprint 1 (R1) | <Defect Name> | N/A | Defect | <Describe the work needed to complete.> | Blocked | Red | 1
Sprint 2 (R1) | Sprint 2 (R1) | [5 empty] | 2 | 75 | 74
Sprint 2 (R1) | <Story name> | Epic 1 | Story | <Describe the story> | Needs Review | Grey | 1
Sprint 2 (R1) | <Task> | Epic 1 | Task | <Describe the work needed to complete.> | Needs Review | Grey | 1
Sprint 3 (R1) | Sprint 3 (R1) | [5 empty] | 4 | 75 | 73
Sprint 3 (R1) | <Story name> | Epic 1 | Story | <Describe the story> | Overdue | Grey | 2
Sprint 3 (R1) | <Task> |  |  | <Describe the work needed to complete.> | Overdue | Grey | 2
Sprint 4 (R1) | Sprint 4 (R1) | [5 empty] | 6 | 75 | 72
Sprint 4 (R1) | <Story name> | Epic 1 | Story | <Describe the story> | Not Started | Grey | 3
Sprint 4 (R1) | <Task> |  |  | <Describe the work needed to complete.> | Not Started | Grey | 3
| Release 2 (R2) | [5 empty] | 22 | 300 | 278
Sprint 1 (R2) | Sprint 1 (R2) | [5 empty] | 4 | 75 | 71
Sprint 1 (R2) | <Story name> | Epic 1 | Story | <Describe the story> | Not Started | Grey | 4
Sprint 1 (R2) | <Task> |  |  | <Describe the work needed to complete.> | Not Started | Grey | 4
Sprint 2 (R2) | Sprint 2 (R2) | [5 empty] | 5 | 75 | 70
Sprint 2 (R2) | <Story name> | Epic 1 | Story | <Describe the story> | Not Started | Grey | 5
Sprint 2 (R2) | <Task> |  |  | <Describe the work needed to complete.> | Not Started | Grey | 5
Sprint 3 (R2) | Sprint 3 (R2) | [5 empty] | 6 | 75 | 69
Sprint 3 (R2) | <Story name> | Epic 1 | Story | <Describe the story> | Not Started | Grey | 6
Sprint 3 (R2) | <Task> |  |  | <Describe the work needed to complete.> | Not Started | Grey | 6
Sprint 4 (R2) | Sprint 4 (R2) | [5 empty] | 7 | 75 | 68
Sprint 4 (R2) | <Story name> | Epic 1 | Story | <Describe the story> | Not Started | Grey | 7
Sprint 4 (R2) | <Task> |  |  | <Describe the work needed to complete.> | Not Started | Grey | 7
Product Backlog
Backlog | Backlog | [5 empty] | 27
Backlog | <Story name> | Epic 1 | Story | <Describe the story> | Not Started |  | 8
Backlog | <Task> | Epic 1 | Task | <Describe the work needed to complete.> | Not Started |  | 8
Backlog | <Story name> | Epic 1 | Story | <Describe the story> | Not Started |  | 9
Backlog | <Task> | Epic 1 | Task | <Describe the work needed to complete.> | Not Started |  | 9
Backlog | <Story name> | Epic 1 | Story | <Describe the story> | Not Started |  | 10
Backlog | <Task> | Epic 1 | Task | <Describe the work needed to complete.> | Not Started |  | 10
CLICK HERE TO CREATE IN SMARTSHEET

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.