## IT Project Gantt Chart
IT PROJECT GANTT CHART TEMPLATE
[ Project Name ]
TASK NAME | START DATE | END DATE | DURATION (days)
Planning | 2022-01-16 | 2022-01-21 | 6
Wireframes | 2022-01-22 | 2022-01-23 | 2
Image Sourcing | 2022-01-22 | 2022-01-28 | 7
Graphics | 2022-01-27 | 2022-01-29 | 3
Design | 2022-01-28 | 2022-02-04 | 8
Search Incorporation | 2022-02-05 | 2022-02-09 | 5
Standards | 2022-01-28 | 2022-02-05 | 9
Legal | 2022-02-04 | 2022-02-06 | 3
Testing | 2022-02-07 | 2022-02-10 | 4
Optimization | 2022-02-09 | 2022-02-12 | 4
Platform Adaptation | 2022-02-11 | 2022-02-14 | 4
App Development | 2022-02-15 | 2022-02-17 | 3
Marketing | 2022-01-28 | 2022-02-05 | 9
Rollout | 2022-02-04 | 2022-02-06 | 3
Documentation | 2022-02-07 | 2022-02-10 | 4
Task 16 | 2022-02-09 | 2022-02-12 | 4
Task 17 | 2022-02-11 | 2022-02-14 | 4
Task 18 | 2022-02-15 | 2022-02-17 | 3
Task 19 | 2022-02-11 | 2022-02-14 | 4
Task 20 | 2022-02-15 | 2022-02-17 | 3
CLICK HERE TO CREATE IN SMARTSHEET
MILESTONE 1:
00/00/00
Brief Description
MILESTONE 2:
00/00/00
Brief Description
MILESTONE 3:
00/00/00
Brief Description
MILESTONE 5:
00/00/00
Brief Description
MILESTONE 4:
00/00/00
Brief Description

## IT Project Gantt Chart BLANK
IT PROJECT GANTT CHART TEMPLATE
[ Project Name ]
TASK NAME | START DATE | END DATE | DURATION (days)
Planning |  |  | 1
Wireframes |  |  | 1
Image Sourcing |  |  | 1
Graphics |  |  | 1
Design |  |  | 1
Search Incorporation |  |  | 1
Standards |  |  | 1
Legal |  |  | 1
Testing |  |  | 1
Optimization |  |  | 1
Platform Adaptation |  |  | 1
App Development |  |  | 1
Marketing |  |  | 1
Rollout |  |  | 1
Documentation |  |  | 1
Task 16 |  |  | 1
Task 17 |  |  | 1
Task 18 |  |  | 1
Task 19 |  |  | 1
Task 20 |  |  | 1
MILESTONE 1:
00/00/00
Brief Description
MILESTONE 2:
00/00/00
Brief Description
MILESTONE 3:
00/00/00
Brief Description
MILESTONE 5:
00/00/00
Brief Description
MILESTONE 4:
00/00/00
Brief Description
Right click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.